## sprint-backlog
QA Agent
no task yet (TBD)
BA Agent
Add versioning on deployment | S | Umi | 2025-11-21 | Completed
Upload storage to blob storage | M | Umi | 2025-11-28 | Completed
Single docker image for UAT and production | M | Umi | 2025-11-28 | Completed
LLM Skill enablement
- SLM - text generation | M | Salman | 2025-11-06 | Completed | demoable app
- SLM - text classification | M | Salman | 2025-11-06 | Completed | demoable app
- compare your trained small model vs a LLM (Claude or GPT) and see which one perform better | M | Salman | 2025-12-05 |  | compare with GPT4
General R&D
Research on LiteLLM routing to multiple LLM providers | M | Umi | 2025-11-03 | Completed | to handle rate limit error issues. Research complete but not yet implemented
Sendo R1 - Dashboard & Report Generation | - | - | - | - | dashboard + mcp server + new kb architecture - combined
1. UI Mockup | M | Sulthan | 2025-11-07 | Completed
2.1 Implement MCP servers for google custom search | M | Sulthan | 2025-11-07 | Completed | to demonstrate capability MCP with external source -> google custom search
2.2 Implement MCP servers for qdrant search as knowledge base search | M | Sulthan | 2025-11-07 | Completed | the result not better than pure rag and slower, but can use to manage complex task
2.3 Implement MCP servers for chat history search as RL feature | M | Sulthan | 2025-11-21 | Completed | for reinforcement learning - no need mcp but from chat history send to input
2.4 Implement MCP servers for dashboard creation | M | Salman | 2025-11-28 | Completed
3. agentic flow to create dashboard | - | - | - | -
3.1 create dynamic multiple agent for create dashboard | L | Salman | 2025-11-21 | Completed
3.2 UI - dashboard creation | L | Salman | 2025-11-21 | Completed | subset of task for - Dashboard Generation. the idea is like "canvas" on gemini
3.3 Dasboard creation for multiple schema - moh report usecase | M | Salman | 2025-12-05 | Completed
4. Knowledge base new architecture | - | - | - | -
4.1.1 Manage content - upload from computer | M | Mayendra | 2025-11-07 | Completed | upload with folder and tags information
4.1.2 Manage content - upload from google drive | M | Umi | 2025-12-05 | Completed
4.2.1 Browse KB - view files | S | Mayendra | 2025-11-14 | Completed | view files with folder and tags information + edit tags capability
4.2.2 Browse KB - download file | S | Mayendra | 2025-11-14 | Completed
4.2.3 Browse KB - view pdf content | S | Mayendra | 2025-11-14 | Completed
4.2.4 Browse KB - view docx, doc, txt, md and other text files content | S | Mayendra | 2025-11-14 | Completed
4.3.1 Chat - Show history | S | Mayendra | 2025-11-21 | Completed
4.3.2 Chat - configurable top k, temperature and model | S | Sulthan | 2025-11-07 | Completed
4.3.3 Chat - knowledge base context based on tags assigned | S | Mayendra | 2025-11-28 | Completed
4.3.4 Access knowledge base files based on tags assigned | S | Mayendra | 2025-12-05 | Completed
4.3.1 Chat - mcp on/off feature | S | Sulthan | 2025-11-07 | Completed
4.3.1 Chat - Fix large text on UI | S | Mayendra | 2025-11-28 | Completed
4.4 Switch knowledge base | M | Mayendra | 2025-11-21 | Completed
4.5.1 KB Settings - user invitation | M | Sulthan | 2025-11-28 | Completed
4.5.2 KB Settings - user privilege setup | M | Sulthan | 2025-11-21 | Completed
4.5.3 KB Settings - role tags assignment | S | Mayendra | 2025-11-28 | Completed
4.5.4 KB Settings - user role assignment | S | Mayendra | 2025-11-28 | Completed
4.6 Notification |  |  | TBD
4.7.1 Super Admin - workspace registration | M | Sulthan | 2025-12-05 | Completed
4.7.2 Super Admin - workspace features registration |  |  | TBD
4.7.2 Super Admin - mcp registration | M | Sulthan | 2025-12-05 | Completed
5. Try claude code to review frontend code (standarize / fix code) | M | Mayendra | 2025-12-05 | Completed
- welcome page |  |  |  | Completed
- theme |  |  |  | Completed
- Localization |  |  |  | Completed
- setup loading while jump to another menu |  |  |  | Completed
Other (just put possible usefull feature here)
rag- Multi-stage pdf extraction with fallbacks |  | Sulthan |  | Completed | current is use fully expensive textract
rag - hybrid retrieval add bm25_search and _rrf_fusion and compare the performance |  | Sulthan |  | Completed
rag- Semantic Caching |  | Sulthan |  | Completed
rag- Agentic Rag |  | Salman |  | Completed
2026-12-01

## product-backlog
Component | Type | Incoming Task From | APP | Feature | Description | Dev Assignment Plan | Status | Start Date | Completed Date | Due Date | MD Estimation | Priority | BD Notes | SG Notes
UX | bugs | BDO | KB Multitentant | files | search not affected to document inside folder | Mayendra | Completed | 2026-01-12 | 2026-01-14 |  | 1 | 1
CORE-AI | rnd | BDO | KB Multitentant | chat | agentic rag not work for ollama with litellm | salman | On Hold |  |  |  | 2 | 2 | ollama agent? langchain agent not working with ollama direct server - for local model use ollama provider (url,api_key), and works only for gpt-oss:20b
CORE-AI | rnd | BDO | KB Multitentant | inference | context window automatically | salman | On Hold |  |  |  | 1 | 2 | max_input_tokens - max_output_tokens - ( system prompt + user prompt + 2 history ) - safety token (500-1000)
CORE-AI | rnd | BDO | BA-Agent | user story | search per context windows | Umi | Completed | 2026-01-12 | 2026-01-14 |  | 2 | 2 | Cannot applied because of output issue
CORE-AI | Refinement | BDO | BA-Agent | user story | Got not relevan result | Umi | Completed | 2026-01-12 | 2026-01-14 |  | 1 | 1
CORE-AI | rnd | BDO | BA-Agent | find module | search per context windows | Umi | Completed | 2026-01-12 | 2026-01-14 |  | 1 | 2 | Cannot applied because of output issue
UX | feature-enhancement | BDO | KB Multitentant | inference | configurable system prompt per workspace and tools | William | On Hold |  |  |  | 1 | 3
UX | feature-enhancement | BDO | KB Multitentant | model | add slm model on kb | Salman | On Hold |  |  |  | 2 | 3
CORE-AI | feature-enhancement | BDO | KB Multitentant | inference | add 2 history on next prompt | Salman | On Hold |  |  |  | 2026-01-02 | 2
CORE-AI | rnd | BDO | BA-Agent | agent | azure tpm issue | Umi | On Hold |  |  |  | 2 | 2 | Implement Queue
CORE-AI | rnd | BDO | QA | agent | azure tpm issue | Mayendra | On Hold |  |  |  | 2 | 2
UX | feature-enhancement | BDO | KB Multitentant | chat | configurable model list per workspace | Mayendra | Completed | 2026-01-12 | 2026-01-14 |  | 2 | 3
CORE-AI | rnd | BDO | KB Multitentant | chat | multiple agent | William | On Hold |  |  |  | 3 | 2
UX | feature-enhancement | BDO | KB Multitentant | login | add manual login with username and password | Mayendra | On Hold |  |  |  | 2 | 3 | Sometimes google sso services or microsoft service down so we need backup plan
CORE-AI | rnd | BDO | QA | model | use local model |  | On Hold |  |  |  |  | 3
CORE-AI | rnd | BDO | BA-Agent | model | use local model |  | On Hold |  |  |  |  | 3
CORE-AI | feature-enhancement | BDO | KB Multitentant | file processor | extract from protected password | Salman | Completed | 2026-01-12 | 2026-01-14 |  | 1 |  | keep protected / release password
UX | feature-enhancement | BDO | KB Multitentant | move current file to folder |  | Mayendra | Completed | 2026-01-12 | 2026-01-14 |  | 1
UX | feature-enhancement | BDO | KB Multitentant | upload file | document versioning | Sulthan | Completed | 2026-01-12 | 2026-01-14 |  |  | 2 | Use existing feature - deep search and chat cognito
CORE-AI | feature-enhancement | BDO | BA-Agent | Upload file | upload pdf robust with multiple stage | Umi | Completed | 2026-01-12 | 2026-01-14
CORE-AI | feature-enhancement | BDo | QA-Agent | Upload file | upload pdf robust with multiple stage | Mayendra | On Hold
| feature-enhancement | SG | TOPPAN Nexus Smart Glossary |  | nexus smart glossary v2 | Salman | On Progress | 2026-01-14 |  |  | 1
| feature-enhancement | SG | TOPPAN Nexus Smart Glossary |  | nexus smart glossary v3 | Salman | On Hold
| changes | SG | TOPPAN Nexus IPO Regulatory |  | Change "Synthesis" to "Issue Summary" | William | On Progress | 2026-01-14
| changes | SG | TOPPAN Nexus IPO Regulatory |  | Change "Ask" to "Suggestive Regulatory Requests" | William | On Progress | 2026-01-14
| feature-enhancement |  | TOPPAN Nexus IPO Regulatory |  | New Ask - Can we add a "reference listing rule" or "relevant regulation" from the HKEX listing rule/SFC regulations to each of the issue? Such will be quite instrumental for user to review how relevant the suggestions may be referring to. Refer to client documents for the listing rules | William | On Hold
| Bugs | SG | TOPPAN Nexus IPO Regulatory |  | The Ref Page are referring to pages not in the Ref Sections (Hallucinating) | William | On Hold
| Bugs | SG | TOPPAN Nexus IPO Regulatory |  | Quote - Is this a direct quote from the prospectus? (Sometimes it seems wrong or hallucinating.) | William | On Hold
| Bugs | SG | TOPPAN Nexus IPO Regulatory |  | For both above issues, we need to try to ensure LLM does not hallucinate, i.e give wrong page numbers, or misquote/completely hallucinate text. In some test documents, Nexus noted that this issue sometimes happens. | William | On Hold
| Bugs | SG | TOPPAN Nexus IPO Regulatory |  | One solution can be to reduce the chapter chunk fed to the LLM. Maybe the prompt context is too long and LLM becomes dumb and starts to not follow instruction/hallucinate/etc. | William | On Hold
| Bugs | SG | TOPPAN Nexus IPO Regulatory |  | Research into eval metrics like ROUGE or BLEU, check with Salman, he has experienced with this, to see if we can set up some short test documents, and repeat the experiment with different chunk sizes, to determine best performance. | William | On Hold
| feature-enhancement | SG | Arc Gen |  | 4.1 Output Generation | Mayendra | On Progress | 2026-01-14
| feature-enhancement | SG | Arc Gen |  | 4.2 Workflow Orchestration | Mayendra | On Hold
| feature-enhancement | SG | Arc Gen |  | 5.1 Automated Comparison | Mayendra | On Hold
| feature-enhancement | SG | Arc Gen |  | 5.2 Manual Review | Mayendra | On Hold
| feature-enhancement | SG | Arc Gen |  | 6.1 Prompt Refinement | Mayendra | On Hold
| feature-enhancement | SG | Arc Gen |  | 6.2 Post-Processing | Mayendra | On Hold
| feature-enhancement | SG | Arc Gen |  | 6.3 Multi-Page Support | Mayendra | On Hold
| Support | SG | KB multitenant |  | Zip sample file and send to priya | Sulthan | Completed | 2026-01-12 | 2026-01-14
| feature-enhancement | SG | KB multitenant |  | Update upload UI to be user friendly | Sulthan | Completed | 2026-01-12 | 2026-01-14
| feature-enhancement | SG | KB multitenant |  | Add button delete, activate/deactivate on admin/users | Sulthan | Completed | 2026-01-12 | 2026-01-14
| feature-enhancement | SG | BA Agent V2 /Sendo |  | Kaizen integration preparation | Umi | On Progress | 2026-01-14
|  | SG | Global App |  | Scalable app Architecture design | Sulthan | On Progress | 2026-01-14

## product list
No | App Name | Status | PM | Code Knowledge Owner | Docs | repository | branch | UAT | Notes
1 | KB-Single tenant | Production | Hanafi | BDO/Sulthan | README.md |  | moh_helpdesk_stg |  | 10 kb released
2 | BA-Agent | Production | Hanafi | BDO/Umi | README.md |  | ba_agent_stg | https://aiaz.uat.toppanecquaria.com/ba-agent
3 | QA-Agent | Production | Hanafi | BDO/Mayendra | README.md |  | qa_agent_stg | https://aiaz.uat.toppanecquaria.com/qa-agent
4 | KB Multitentant | UAT | Hanafi | BDO/Sulthan | TECHNICAL_DOCUMENTATION.md |  | feature/kb_enhacement
5 | SLM | rnd | - | BDO/Salman | README.md
6 | Dashboard Agent | rnd | - | BDO/Salman | README.md
7 | HDB AI Preparation | UAT | - | BDO/Salman | clone from kb but different config |  | gpu_deployment
8 | TOPPAN Nexus Smart Glossary | Development | Hanafi | Hanafi --> salman | CLAUDE.md CHANGELOG.md | https://hub.ecquaria.com/gitlab/inov8/nexus-smart-glossary | version2 | https://aiaz.uat.toppanecquaria.com/nexussmartglossary | Some changes requested by client (Toppan Nexus). (Actually, I made a demo and sent them, and then they just gave their requirements/specs. Need to revised according to their specs) Uses classical NLP NER (Named Entity Recognition) plus LLM, someone stronger in NLP may be better suited for this. | https://drive.google.com/file/d/19kndn9bcwDevpKObVVhVGgkRy1F9ofO_/view?usp=drive_link
9 | TOPPAN Nexus IPO Regulatory | Development | Hanafi | Hanafi --> william | CLAUDE.md CHANGELOG.md | https://hub.ecquaria.com/gitlab/inov8/nexus-ipoqueries | main | https://aiaz.uat.toppanecquaria.com/nexusipo | Client wants some formatting changes for now. This project maybe is closer to completion.
10 | arch gen | Development | Hanafi | Hanafi --> mayendra | INSTRUCTION.MD, WORK_PLAN.MD | https://hub.ecquaria.com/gitlab/inov8/enterpriseagents/arch-gen | main |  | lower priority because is just in house TECQ use case, not external client
11 | BA Agent V2 /Sendo | Upcoming | Hanafi | --> Umi | Integration with kaizen
12 | TOPPAN Next Tech (Printing) | Upcoming 2/3 project | Ang Kang |  | TBD
13 | QA-Agent V2/Sendo | Upcoming | Priya |  | TBD